## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date: | 2023-01-31
Current Sprint: | 56
Time Period | Time Period End | Features allocation, % | Development Sprints available | Points / sprint | Capacity | Comments
2023 Q1 | 2023-03-28 | 50% | 4 | 200 | 400
2023 Q2 | 2023-06-30 | 60% | 6.5 | 200 | 780
2023 H2 | 2023-12-31 | 50% | 13.5 | 200 | 1350
2024 | 2024-12-31 | 50% | 26.5 | 200 | 2650
Formulas:
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM(B3,1))/2
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM([Time Period End, row above],1))/2

## Capacity
Delivery | Planned | Available
2023 Q1 | 0 | 500
2023 Q2 | 0 | 100
2023 H2 | 0 | 300
2024 | 0 | 600