## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date: | 2023-02-28
Current Sprint: | 56
Time Period | Time Period End | Features allocation, % | Development Sprints available | Points / sprint | Capacity | Comments
2023 Q1 | 2023-03-28 | 80% | 2 | 200 | 320
2023 Q2 | 2023-06-30 | 70% | 6.5 | 200 | 910
2023 Q3 | 2023-09-30 | 50% | 6.5 | 200 | 650
2023 Q4 | 2023-12-31 | 50% | 7 | 200 | 700
2024 | 2024-12-31 | 50% | 26.5 | 200 | 2650
Formulas:
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM(B3,1))/2
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM([Time Period End, row above],1))/2

## Capacity
Delivery | Planned | Available | Functionality: Tactical | Maintenance | Operations: Security | Operations: Effectiveness | Usability | Performance | Functionality: Strategic | Not specified
2023 Q1 | 390 | 320 | 0 | 30 | 20 | 20 | 40 | 50 | 210 | 20
2023 Q2 | 910 | 910 | 190 | 30 | 0 | 160 | 140 | 0 | 390 | 0
2023 Q3 | 980 | 650 | 190 | 50 | 150 | 80 | 180 | 60 | 270 | 0
2023 Q4 | 160 | 700 | 0 | 0 | 0 | 0 | 130 | 30 | 0 | 0
2024 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GITHUB_EPICS
Assignees | Repository | Labels | Title | Status | EpicPoints | SprintPoints | Period | Sprint | Type | Partner | Assignees | Release
Andrew Pazniak | alkemio | Epic,UX | Landing page v1 | Done | 50 | 20 | 2023 Q1 | 2023-02-14 | Functionality: Strategic
Aleksandar Stojanovic | alkemio | Epic | User to user communication via notifications | Done | 80 | 10 | 2023 Q1 | 2023-02-14 | Functionality: Tactical | UWV | 60
| alkemio | Epic | Calendar Events per community | Done | 50 | 80 | 2023 Q1 | 2023-01-17 | Functionality: Tactical | UWV | Aleksandar Stojanovic
| alkemio | Epic | Capacity Planning | Done | 10 | 10 | 2023 Q1 | 2023-01-31 | Maintenance | 30 | Svetoslav Petkov | Release 230208
Svetoslav Petkov | alkemio | Epic | Reporting: Northstar Metric | Done | 50 | 30 | 2023 Q1 | 2023-01-31 | Functionality: Strategic | 30 | 30
| alkemio | Epic | UX Refinements: Round 2 | Done | 30 | 30 | 2023 Q1 | 2023-01-03 | Functionality: Tactical | 20 | Andrew Pazniak | Release 230208
| alkemio | Epic | UX Refinements - Round 3 | Defined | 20 | 30 | 2023 Q1 | 2023-02-14 | Usability | 30
Rene Honig,Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Security: Authentication via Microsoft identities - basic | Defined | 20 | 20 | 2023 Q1 | 2023-02-14 | Operations: Security | 20 | Rene Honig,Valentin Yanakiev
Valentin Yanakiev | alkemio | Epic,Infrastructure | Custom URL for Demo Hubs on production | Being elaborated | 80 | 30 | 2023 Q1 | 2023-02-14 | Functionality: Strategic | 30 | Valentin Yanakiev
Valentin Yanakiev | alkemio | Epic,UX,client | Search++: Within a Hub, Contributions, UI | Done | 30 | 20 | 2023 Q1 | 2023-02-14 | Functionality: Tactical | UWV, VNG | Valentin Yanakiev
| alkemio | Epic,UX | Innovation Spaces: Specified Communities + visuals | Being defined | 80 | 10 | 2023 Q1 | 2023-03-14 | Functionality: Strategic | UWV | 30
Carlos Cano | alkemio | Epic | Calendar Events V2 | Done | 30 | 20 | 2023 Q1 | 2023-02-14 | Functionality: Tactical | UWV | Carlos Cano
Svetoslav Petkov | alkemio | Epic | Community forum on the platform | Defined | 20 | 10 | 2023 Q1 | 2023-02-14 | Functionality: Strategic | 10 | Svetoslav Petkov
Valentin Yanakiev | alkemio | Epic | Domain model: Naming alignment | Being elaborated | 30 | 30 | 2023 Q2 | 2023-02-28 | Maintenance |  | Valentin Yanakiev
Valentin Yanakiev | server | Epic,server | Domain Model: Profiles | Defined | 30 | 20 | 2023 Q1 | 2023-02-14 | Maintenance | 20 | Valentin Yanakiev
Svetoslav Petkov | alkemio | Epic | Handling of Time | Being elaborated | 30 | 10 | 2023 Q2 | 2023-02-14 | Usability | 10 | Svetoslav Petkov
| alkemio | Epic,UX | UX Refinements - Round 4 | Being elaborated | 30 | 30 | 2023 Q2 |  | Usability | Andrew Pazniak
Andrew Pazniak | alkemio | Epic,UX | Contributor visibility | Defined | 30 | 30 | 2023 Q3 |  | Functionality: Tactical |  | Andrew Pazniak
| alkemio | Epic,UX | Contribute Page | Being elaborated | 30 | 30 | 2023 Q3 |  | Usability
| alkemio | Epic,UX | Whiteboard: Usability v1 | Being elaborated | 30 | 30 | 2023 Q2 |  | Functionality: Tactical
| alkemio | Epic,UX | Hub visibility for unauthorized users | Being elaborated | 30 | 30 | 2023 Q3 |  | Usability
Valentin Yanakiev | alkemio | Epic | Release mgmt: Documentation, process + split | Being elaborated | 50 | 50 | 2023 Q2 | 2023-02-28 | Operations: Effectiveness |  | Valentin Yanakiev
Valentin Yanakiev | alkemio | Epic | Error Handling: Presentation improvements | Being elaborated | 30 | 30 | 2023 Q3 |  | Usability | Valentin Yanakiev | Valentin Yanakiev
| alkemio | Epic | Whiteboard: interactive multi-user editing | Being elaborated | 80 | 20 | 2023 Q2 |  | Functionality: Strategic | 20 | 20
| alkemio | Epic | Community Terms + Conditions | Icebox | 80 | 50 | 2023 Q2 |  | Functionality: Strategic
| alkemio | Epic | Documents: Wider usage, Management and limits | Icebox | 50 | 50 | 2023 Q2 |  | Functionality: Strategic
| alkemio | Epic | Documents: Storage with privacy | Icebox | 50 | 50 | 2023 Q2 |  | Functionality: Tactical
| alkemio | Epic | Keyboard navigation | Icebox | 50 | 50 | 2023 Q3 |  | Usability
| alkemio | Epic | Performance: Dataloaders / field resolvers | Being elaborated | 50 | 30 | 2023 Q1 |  | Performance | 30 | Valentin Yanakiev
| alkemio | Epic,UX | Comments: Improved interaction | Icebox | 30 | 30 | 2023 Q2 |  | Functionality: Tactical
Svetoslav Petkov | alkemio | Epic,UX | Library: Innovation Pack management | Parked | 50 | 50 | 2023 Q3 |  | Functionality: Strategic | Svetoslav Petkov | Svetoslav Petkov
Rene Honig,Valentin Yanakiev | alkemio | Epic | Security: Kubernetes hardening | Icebox | 50 | 50 | 2023 Q3 |  | Operations: Security | Rene Honig,Valentin Yanakiev | Rene Honig,Valentin Yanakiev
| alkemio | Epic | Security: Control of provider per organization | Icebox | 50 | 50 | 2023 Q3 |  | Functionality: Tactical
Valentin Yanakiev | alkemio | Epic | Infrastructure: Maintainability | Icebox | 50 | 50 | 2023 Q3 |  | Operations: Effectiveness |  | Valentin Yanakiev
| alkemio | Epic | Login Refinements / Kratos | Icebox | 30 | 30 | 2023 Q3 |  | Operations: Security
Rene Honig,Valentin Yanakiev | hub | Epic,operations | Security: Client code execution / injection | Icebox | 30 | 30 | 2023 Q3 |  | Operations: Security | Rene Honig,Valentin Yanakiev | Rene Honig,Valentin Yanakiev
| alkemio | Epic,UX | Grouping of Hubs by theme | Done | 20 | 10 | 2023 Q1 | 2023-02-14 | Functionality: Strategic | 10
Denise Larsson | alkemio | Epic,UX | Invitations to Hub | Parked | 50 | 50 | 2023 Q3 |  | Functionality: Tactical | Denise Larsson | Denise Larsson
| alkemio | Epic | Reporting: Sharing of analysis | Parked | 20 | 20 | 2023 Q2 | 2023-03-14 | Operations: Effectiveness
| alkemio | Epic,UX | Hub Visualization component | Parked | 30 | 30 | 2023 Q3 |  | Functionality: Strategic
| alkemio | Epic | Ecosystem Analytics: prototype | New | 80 | 80 | 2023 Q3 |  | Functionality: Strategic
Carlos Cano | alkemio | Epic | Visuals on Journeys: Enhanced selection + suggested imageswith alternative text | New | 30 | 30 | 2023 Q2 | Envision | Usability | Envision | Carlos Cano
| alkemio | Epic | Image upload + storage | New | 30 | 30 | 2023 Q3 |  | Functionality: Tactical
| alkemio | Epic,UX | Journey Pages structure roadmap | New | 50 | 50 | 2023 Q2 |  | Functionality: Strategic
| alkemio | Epic | Matrix adapter as a separate service | Done | 50 | 40 | 2023 Q1 | 2023-01-03 | Maintenance | 40 | 40
Neil Smyth | alkemio | Epic | Private challenges | Done | 50 | 30 | 2023 Q1 | 2023-01-03 | 2023-01-03 | 30 | Neil Smyth
Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Kratos 0.11 Update | Done | 50 | 50 | 2023 Q1 | 2023-01-17 | Operations: Security |  | Valentin Yanakiev
Aleksandar Stojanovic | alkemio | Epic | Callout: single canvas type | Done | 30 | 30 | 2023 Q1 | 2023-01-17 | 2023-01-17 |  | Aleksandar Stojanovic
| alkemio | Epic | Data Integrity | Done | 50 | 50 | 2023 Q1 | 2023-01-17 | Maintenance
| alkemio | Epic,UX | Callouts in context | New | 30 | 30 | 2023 Q2 |  | Functionality: Strategic | UWV
| alkemio | Epic | Demo environment data migration + retirement | New | 10 | 20 | 2023 Q2 |  | Operations: Effectiveness
| alkemio | Epic | Choral Explanations | New | New |  | TIP | TIP | Functionality: Strategic | TIP
Svetoslav Petkov | alkemio | Epic | Smart search v1 | New | 80 | 80 | 2023 Q3 | UWV | Functionality: Strategic | UWV | Svetoslav Petkov
| alkemio | Epic,UX | Community tab in Hub menu | New | 20 | 20 | 2023 Q1 |  | Usability
| homepage | UX,Epic | Landing page: refinements + maintainability | New | 30 | 30 | 2023 Q1 | 2023-02-28 | Functionality: Strategic |  | Valentin Yanakiev
| alkemio | Epic | QA Test suites catchup | In progress | 50 | 20 | 2023 Q3 | 2023-02-14 | Maintenance | 20
| alkemio | Epic | Notifications dashboard | Being defined | 30 | 30 | 2023 Q2 |  | Functionality: Tactical
Valentin Yanakiev | alkemio | Epic | Release mgmt: release notes + changelog | New | 30 | 30 | 2023 Q3 |  | Operations: Effectiveness |  | Valentin Yanakiev
Valentin Yanakiev | alkemio | Epic | Operations: Platform monitoring | New | 30 | 30 | 2023 Q2 | 2023-02-14 | Operations: Effectiveness | 20 | Valentin Yanakiev
Svetoslav Petkov | alkemio | Epic | Reporting: Platform usage insights | New | 20 | 20 | 2023 Q1 | 2023-02-14 | Operations: Effectiveness | 10 | Svetoslav Petkov
Valentin Yanakiev | alkemio | Epic | Data Integrity: v2 | New | 30 | 30 | 2023 Q2 |  | Operations: Effectiveness |  | Valentin Yanakiev
Valentin Yanakiev | infrastructure-operations | security,Epic | Security: Secret management | New | 20 | 20 | 2023 Q3 |  | Operations: Security |  | Valentin Yanakiev
Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Operational security analysis | New | 20 | 20 | 2023 Q3 |  | Operations: Security |  | Valentin Yanakiev
Valentin Yanakiev | alkemio | Epic | Operations: Kratos, Cluster Health | New | 20 | 20 | 2023 Q2 |  | Operations: Effectiveness |  | Valentin Yanakiev
Svetoslav Petkov | alkemio | Epic,UX | Branding at platform level | New | 30 | 30 | 2023 Q2 |  | Functionality: Strategic |  | Svetoslav Petkov
| alkemio | Epic | Innovation spaces: readiness for release | New | 50 | 50 | 2023 Q2 |  | Functionality: Strategic
| client-web | epic,client,UX | Knowledge Management in journeys | New | 30 | 30 | 2023 Q3 |  | Functionality: Tactical
| alkemio | Epic,A: Community | Engagement: user newsletter signup during registration | New | 20 | 20 | 2023 Q2 |  | Functionality: Strategic
| alkemio | Epic,UX,client | Update of Journey settings tab | New | 20 | 30 | 2023 Q2 |  | Usability
| alkemio | Epic | Search results validated in service | New | 30 | 30 | 2023 Q4 |  | Performance
| alkemio | Epic | Accessibility Gap Analysis | New | 30 | 30 | 2023 Q2 |  | Usability
| alkemio | Epic | Innovation library usage | New | 30 | 30 | 2023 Q3 |  | Functionality: Strategic
| alkemio | Epic | Sharing: social media | New | 20 | 20 | 2023 Q3 |  | Usability
| alkemio | Epic | Follow a Hub / Challenge / Opportunity | New | 50 | 50 | 2023 Q4 |  | Usability
| alkemio | Epic | Preference for aggregated of notifications | New | 80 | 80 | 2023 Q4 |  | Usability
| alkemio | Epic | User to user messaging via message box | New | 50 | 50 | 2023 Q2 |  | Functionality: Tactical
| alkemio | Epic,QA | Performance + scalability testing | New | 30 | 30 | 2023 Q3 |  | Performance
| alkemio | Epic,UX | Callouts: Sorting control | New | 20 | 20 | 2023 Q3 |  | Usability |  | Carlos Cano
| server | Epic,server | Server: Performance Optimization | New | 30 | 30 | 2023 Q3 |  | Performance
| alkemio | Epic | Search in Contribute page | Being elaborated | 20 |  | 2023 Q1 |  |  | UWV | Valentin Yanakiev,Denise Larsson
| alkemio | Epic | Callout: Survey / voting | New
| alkemio | Epic | Callout templates | New
| alkemio | Epic | Callout: Jobs to be done | New
| alkemio | client | Add Callout title + description to Card/Canvas creation | New
| alkemio | Epic,UX | Innovation Flow to include goal/checklist/callouts | New
| alkemio | Epic | Operations: Kratos, Cluster Health | New | 2023 Q2 | 20 | 20 |  | Operations: Effectiveness |  | Valentin Yanakiev