## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date: | 2023-01-31
Current Sprint: | 56
Time Period | Time Period End | Features allocation, % | Development Sprints available | Points / sprint | Capacity | Comments
2023 Q1 | 2023-03-28 | 50% | 4 | 200 | 400
2023 Q2 | 2023-06-30 | 60% | 6.5 | 200 | 780
2023 H2 | 2023-12-31 | 50% | 13.5 | 200 | 1350
2024 | 2024-12-31 | 50% | 26.5 | 200 | 2650
Formulas:
Development Sprints available = (WEEKNUM([Time Period End])-WEEKNUM(B3))/2
Development Sprints available = (WEEKNUM([Time Period End])-WEEKNUM([Time Period End, row above]))/2

## Capacity
Delivery | Planned | Available
2023 Q1 | 260 | 500
2023 Q2 | 500 | 100
2023 H2 | 0 | 300
2024 | 400 | 600

## GITHUB_EPICS
Filter criteria: - repo: Alkemio - label: Epic - pipeline: Not closed |  |  |  | TBD - Use labels for initiatives? - Resource type breakdown per Epic - Make use of backlog ranking? + where? - Plan per team or in aggregate?
ID | Title | Assigned To | State | Initiative | Period | Estimate - Original | Estimate - Remaining | Effort - Done | Activity Type
2447 | Release mgmt | Valentin Yanakiev | Being Elaborated | User Engagement | 2023 Q1 |  | 260 |  | Maintenance
2332 | Connections: tags / mentions | Andrew Pazniak | Being Elaborated | Maintainability | 2023 Q2 |  | 500 |  | Enhancement
2222 | Innovation Spce: routing | Valentin Yanakiev | New | Well sections | 2024 |  | 400 |  | New development