## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date:
Current Sprint: | 56
Time Period | Time Period Start | Time Period End | Features allocation, % | Development Sprints available | Vacations / Done (sprints) | Available Sprints | Points / sprint | Capacity | Comments
2023 Q1 | 2023-01-02 | 2023-03-27 | 80% | 6 |  | 6 | 200 | 960
2023 Q2 | 2023-03-27 | 2023-07-03 | 80% | 7 | 4 | 3 | 200 | 480 |  | Note: update to have each period start / end adjustable
2023 Q3 | 2023-07-03 | 2023-09-25 | 50% | 6 | 1 | 5 | 200 | 500
2023 Q4 | 2023-09-25 | 2024-01-01 | 50% | 7 | 0.5 | 6.5 | 200 | 650
2024 | 2024-01-01 | 2024-12-31 | 50% | 26.0714 |  | 26.0714 | 200 | 2607.1429
Formulas:
Time Period Start = [Time Period End, row above]

## Capacity
Delivery | Planned | Available | Done | Functionality: Tactical | Maintenance | Operations: Security | Operations: Effectiveness | Usability | Performance | Functionality: Strategic | Not specified
2023 Q1 | 0 | 960 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023 Q2 | 580 | 480 | 380 | 110 | 20 | 0 | 170 | 100 | 0 | 180 | 0
2023 Q3 | 720 | 500 | 0 | 50 | 0 | 0 | 20 | 260 | 0 | 230 | 160
2023 Q4 | 1020 | 650 | 0 | 170 | 50 | 160 | 130 | 100 | 90 | 290 | 30
2024 | 0 | 2607.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GITHUB_EPICS
Repository | Labels | Title | Status | Type | EpicPoints | Period | Sprint | SprintPoints | Assignees | Partner | Milestone
alkemio | Epic | Innovation library management by admins | Done | Functionality: Strategic | 20 | 2023 Q2 | 2023-03-28 | 20
alkemio | Epic | UX Refinements - Round 3 | Done | Usability | 30 | 2023 Q1 | 2023-03-14 | 10
alkemio | Epic,client | Search++: Within a Hub, Contributions, UI | Done | Functionality: Tactical | 30 | 2023 Q1 | 2023-02-14 | 20 | Valentin Yanakiev | UWV, VNG
server | Epic,server | Domain Model: Profiles | Done | Maintenance | 80 | 2023 Q1 | 2023-03-14 | 80 | Valentin Yanakiev
alkemio | Epic | Community forum on the platform | Done | Functionality: Strategic | 20 | 2023 Q1 | 2023-03-14 | 10 | Svetoslav Petkov
alkemio | Epic,UX | Landing page v1 | Done | Functionality: Strategic | 50 | 2023 Q1 | 2023-02-14 | 20 | Andrew Pazniak
alkemio | Epic | Improved content editing | Done | Usability | 50 | 2023 Q1 | 2023-02-28 |  |  | TNO
alkemio | Epic | User to user communication via notifications | Done | Functionality: Tactical | 80 | 2023 Q1 | 2023-02-14 | 10 | Aleksandar Stojanovic | UWV
alkemio | Epic | Community Application Questions | Done | Functionality: Tactical | 10 | 2023 Q1 | 2023-02-28
alkemio | Epic | Calendar Events V2 | Done | Functionality: Tactical | 30 | 2023 Q1 | 2023-02-14 | 20 | Carlos Cano | UWV
alkemio | Epic,UX | Grouping of Hubs by theme | Done | Functionality: Strategic | 20 | 2023 Q1 | 2023-02-14 | 10
alkemio | Epic | Calendar Events per community | Done | Functionality: Tactical | 50 | 2023 Q1 |  |  |  | UWV
alkemio | Epic | Capacity Planning | Done | Maintenance | 10 | 2023 Q1 |  | 10
alkemio | Epic | Reporting: Northstar Metric | Done | Functionality: Strategic | 50 | 2023 Q1 |  | 30 | Svetoslav Petkov |  | Core Capabilities
alkemio | Epic | UX Refinements: Round 2 | Done | Functionality: Tactical | 30 | 2023 Q1 |  | 30
alkemio | Epic,A: Platform,Infrastructure | Custom URL for Demo Hubs on production | Done | Functionality: Strategic | 80 | 2023 Q2 | 2023-04-11 | 30 | Valentin Yanakiev
alkemio | Epic | Hub visibility for unauthorized users | Done | Usability | 10 | 2023 Q1 | 2023-03-28 | 10
alkemio | Epic,UX | Email Templates: Refresh, multi-language | Being elaborated | Usability | 50 | 2023 Q3 |  |  |  | UWV
alkemio | Epic,UX | Comments: Threads + replies | Being defined | Functionality: Tactical | 30 | 2023 Q2 | 2023-05-09
alkemio | Epic | Smart search v1 | Icebox | Functionality: Strategic | 80 | 2023 Q4 |  |  | Svetoslav Petkov | UWV
alkemio | Epic | Choral Explanations | Icebox | Functionality: Strategic |  | 2023 Q4 |  |  |  | TIP
alkemio | Epic | Sharing: social media | Icebox | Usability | 20 | 2023 Q4
alkemio | Epic,UX | Hide / turn functionalities off | Icebox | Usability |  | 2023 Q4
alkemio | Epic | Integration of other online tools | Icebox | Functionality: Strategic |  | 2023 Q4
alkemio | Epic | Callouts: Sorting control | Done | Usability | 20 | 2023 Q1 | 2023-03-14 | 10
infrastructure-operations | operations,Epic,Infrastructure | Operational security analysis | Icebox | Operations: Security | 20 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Initiative | I: Analytics via connectivity graph v1 | Icebox
alkemio | Epic | Visuals on Journeys: Enhanced selection + suggested images | Icebox | Usability | 30
alkemio | Epic | Performance: Dataloaders / field resolvers | Done | Performance | 50 | 2023 Q1 | 2023-03-14 | 20
client-web | epic,client | Client: Developer documentation, roadmap | Current / next quarter | Operations: Effectiveness | 20 | 2023 Q4
alkemio | Epic | Reporting: Platform usage insights | Current / next quarter | Operations: Effectiveness | 20 | 2023 Q3 |  |  | Svetoslav Petkov
alkemio | Epic | Release mgmt: release notes + changelog | Current / next quarter | Operations: Effectiveness | 30 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Epic,Roadmap Candidate | UX Refinements Round 5 | Current / next quarter | Usability | 30 | 2023 Q3
alkemio | Epic,Roadmap Discussion | Accessibility: Keyboard navigation | Current / next quarter | Usability | 30 | 2023 Q3 |  |  |  | Envision
alkemio | Epic,UX | Contributor visibility | Current / next quarter | Functionality: Tactical | 30 | 2023 Q4 |  |  | Andrew Pazniak
alkemio | Epic | Whiteboard: interactive multi-user editing | Being elaborated | Functionality: Strategic | 80 | 2023 Q2 |  | 20
alkemio | Epic | Data Integrity: v2 | Current / next quarter | Operations: Effectiveness | 30 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Epic | Security: Kubernetes hardening | Current / next quarter | Operations: Security | 50 | 2023 Q4 |  |  | Rene Honig,Valentin Yanakiev
server | Epic,server | Server: Performance Optimization | Current / next quarter | Performance | 30 | 2023 Q4
alkemio | Epic,UX | Whiteboard: Usability v1 | Current / next quarter | Functionality: Tactical | 30 | 2023 Q4
alkemio | Epic | Client errors tracability | Being elaborated | Operations: Effectiveness | 20 | 2023 Q2 | 2023-06-06 | 10
alkemio | Epic | Handling of Time | Current / next quarter | Usability | 30 | 2023 Q4 |  | 10 | Svetoslav Petkov
alkemio | Epic | Release mgmt: Documentation, process + split | Being elaborated | Operations: Effectiveness | 50 | 2023 Q2 | 2023-06-06 |  | Valentin Yanakiev
alkemio | Epic | Demo environment data migration + retirement | Done | Operations: Effectiveness | 10 | 2023 Q1 | 2023-03-14
alkemio | Epic,Security | Security headers hardening | Current / next quarter | Operations: Security | 10 | 2023 Q4
alkemio | Epic,A: Platform | Innovation spaces: readiness for release | Current / next quarter | Functionality: Strategic | 50 | 2023 Q4 |  |  |  | UWV, Digicampus
alkemio | Epic,UX | Innovation Flow to include goal/checklist/callouts | Current / next quarter | Functionality: Strategic | 80 | 2023 Q3 |  |  |  | UWV
alkemio | Epic,UX | Library: Innovation Pack management | Current / next quarter | Functionality: Strategic | 50 | 2023 Q3 |  |  | Svetoslav Petkov
alkemio | Epic | User to user messaging via message box | Current / next quarter | Functionality: Tactical | 50 | 2023 Q3
alkemio | Epic,UX | Invitations to Hub | Being elaborated | Functionality: Tactical | 50 | 2023 Q2 |  |  | Valentin Yanakiev,Denise Larsson
alkemio | Epic,Roadmap Candidate | Analytics + monitoring: Dedicated elastic cluster | Being elaborated | Operations: Effectiveness | 30 | 2023 Q2
alkemio | Epic | Operations: Platform monitoring | Current / next quarter | Operations: Effectiveness | 30 | 2023 Q2 |  |  | Valentin Yanakiev
alkemio | Epic,UX,client,A: Context | Update of Journey settings tab | Current / next quarter | Usability | 20 | 2023 Q2 |  |  |  | UWV
alkemio | Epic | Community Terms: phase 1 - library support, simple templates | Current / next quarter | Functionality: Strategic | 50 | 2023 Q2 | 2023-06-06 |  |  | Digicampus, Den Haag
alkemio | Epic | Operations: Kratos, Cluster Health | Current / next quarter | Operations: Effectiveness | 20 | 2023 Q2 |  |  | Valentin Yanakiev
alkemio | Epic,UX,A: Platform | Branding at platform level | Current / next quarter | Functionality: Strategic | 30 | 2023 Q4 |  |  | Svetoslav Petkov | UWV, Digicampus
alkemio | Epic | Ecosystem Analytics: prototype | Current / next quarter | Functionality: Strategic | 80 | 2023 Q4 |  |  |  | UWV
alkemio | Epic,A: Community | Engagement: user newsletter signup during registration | Current / next quarter | Functionality: Strategic | 20 | 2023 Q4
alkemio | Epic | Notifications dashboard | Current / next quarter | Functionality: Tactical | 30 | 2023 Q2
alkemio | Epic | Matrix adapter as a separate service | Done | Maintenance | 50 | 2023 Q1 |  | 40
alkemio | Epic | Private challenges | Done | Functionality: Strategic | 50 | 2023 Q1 |  | 30 | Neil Smyth
infrastructure-operations | operations,Epic,Infrastructure | Kratos 0.11 Update | Done | Operations: Security | 50 | 2023 Q1 |  |  | Valentin Yanakiev
alkemio | Epic | Callout: single canvas type | Done | Usability | 30 | 2023 Q1 |  |  | Aleksandar Stojanovic
alkemio | Epic | Data Integrity | Done | Maintenance | 50 | 2023 Q1
alkemio | Epic,A: Context | New hub structure with callouts in context | Done | Usability | 80 | 2023 Q2 | 2023-04-25 | 80 |  | UWV
alkemio | Epic | Forum: notifications, sharing | Done | Functionality: Tactical | 20 | 2023 Q2 | 2023-04-25
alkemio | Epic | Accessibility: Visuals alternative text | Done | Usability | 30 | 2023 Q2 | 2023-04-11 |  |  | UWV, Envision, Gebruiker Centraal
alkemio | Epic | QA Test suites catchup | In progress | Maintenance | 50 | 2023 Q4 | 2023-03-14 | 20
alkemio | Epic | Domain model: Naming alignment | Defined | Maintenance | 20 | 2023 Q2 | 2023-05-23 |  | Valentin Yanakiev
alkemio | Epic | Error Handling: Presentation improvements | Current / next quarter | Usability | 30 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Epic,UX | Search in Contribute page | Icebox | Usability | 20 | 2023 Q4 |  |  |  | UWV
infrastructure-operations | operations,Epic,Infrastructure | Security: Authentication via Microsoft identities - basic | Done | Operations: Security | 20 | 2023 Q2 | 2023-04-11 | 20 | Rene Honig,Valentin Yanakiev
landingpage | Epic | Landing page: refinements + maintainability | Done | Functionality: Strategic | 30 | 2023 Q1 | 2023-03-28 | 10
alkemio | Epic,UX | UX Refinements - Round 4 | Defined | Usability | 30 | 2023 Q2
alkemio | Epic | Search: Additional contiribution types | Current / next quarter | Functionality: Tactical | 30 | 2023 Q4 |  |  |  | UWV
alkemio | Epic,UX | Multiple Lead Organizations on Hub | Current / next quarter | Functionality: Strategic | 20 | 2023 Q3 |  |  |  | Shipping Retrofits, TIP
alkemio | Epic | Landing page V1.2 | Current / next quarter | Functionality: Tactical | 30 | 2023 Q4
alkemio | Epic | User controls on data visibility | New |  |  | 2023 Q4
alkemio | Epic | Calendar events V3 | Current / next quarter | Functionality: Tactical |  | 2023 Q4 |  |  |  | UWV
alkemio | Epic | Reporting: Operational monitoring, usage of northstar metrics | Elaborated | Operations: Effectiveness | 20 | 2023 Q2 | 2023-05-23
alkemio | Epic | Smart Analytics to understand community needs/interests | New |  |  | 2023 Q3 |  |  |  | UWV
alkemio | Epic | Sharing metrics of Hub activity with Hub leads | New | [6 empty] | UWV
alkemio | Epic | Definitions for URLs | New
alkemio | Epic | Multiple email support | New
alkemio | Epic | Preference for aggregated of notifications | Current / next quarter | Usability | 80 | 2023 Q3
alkemio | Epic,UX | Hub Visualization component | Current / next quarter | Functionality: Strategic | 30 | 2023 Q4
alkemio | Epic | Infrastructure: Maintainability | Current / next quarter | Operations: Effectiveness | 50 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Epic | Follow a Hub / Challenge / Opportunity | Current / next quarter | Usability | 50 | 2023 Q3
alkemio | Epic | Search results validated in service | Current / next quarter | Performance | 30 | 2023 Q4
alkemio | Epic,QA | Performance + scalability testing | Current / next quarter | Performance | 30 | 2023 Q4
hub | Epic,operations | Security: Client code execution / injection | Current / next quarter | Operations: Security | 30 | 2023 Q4 |  |  | Rene Honig,Valentin Yanakiev
infrastructure-operations | security,Epic | Security: Secret management | Current / next quarter | Operations: Security | 20 | 2023 Q4 |  |  | Valentin Yanakiev
alkemio | Epic | Login Refinements / Kratos | Current / next quarter | Operations: Security | 30 | 2023 Q4
alkemio | Epic | Security: Control of provider per organization | Current / next quarter | Functionality: Tactical | 50 | 2023 Q4
alkemio | Epic,Roadmap Discussion | Images in markdown | Current / next quarter | Usability | 20 | 2023 Q3
alkemio | Epic,UX | Innovation Flow Visual Refresh | New
alkemio | Epic,Roadmap Discussion | Simple Challenge version | New | [6 empty] | uwv
alkemio | Epic,UX,A: Context | Journey refresh: Hub level additional functionality | In progress | Usability | 50 | 2023 Q2 | 2023-05-23
alkemio | Epic,Roadmap Discussion | Platform navigation | New
alkemio | Initiative | I: Journey structure refresh | New |  |  |  | 2023-03-14 |  | Denise Larsson
alkemio | Initiative | I: Maintainability | New
alkemio | Initiative | I: Innovation library - Agreements | New
alkemio | Initiative | I: Onboarding the community | New
alkemio | Initiative | I: Whiteboard Usage | New
alkemio | Initiative | I: Innovation Spaces | New
alkemio | Initiative | I: Guidance for users | New
alkemio | Initiative | I: Platform responsiveness | New
alkemio | Initiative | I: Platform Management | New
alkemio | Initiative | I: Content + Knowledge Management | New
alkemio | UX,Initiative | I: Accessibility | New
alkemio | Initiative | I: Reporting on Usage | New
alkemio | Initiative | I: Notifications | New
alkemio | Initiative | I: Library population, usage + feedback | New
alkemio | Initiative | I: Content on the platform | New
alkemio | Initiative | I: Innovation Library | New
alkemio | Initiative | I: Enriched User Profiles | New
alkemio | Initiative | I: Smart search | New
alkemio | Initiative | I: Whiteboards to generate content | New |  |  | 2023 Q4
alkemio | Initiative | I: My Activity Feed | New |  |  | 2023 Q4
alkemio | Initiative | I: Community Inclusion Tools | New |  |  | 2023 Q4
alkemio | Initiative | I: Connecting on Platform | New |  |  | 2023 Q1
alkemio | Initiative | I: Usability/User experience refinement? | New |  |  | 2023 Q1
alkemio | Initiative | I: Landing page | New |  |  | 2023 Q1
alkemio | Initiative | I: Engaging the community | New |  |  | 2023 Q1
hub | Epic | License / Subscription management v1: (quotas) | Current / next quarter |  | 80 | 2023 Q3
alkemio | Epic | Community Terms: phase 2 | New |  | 30 | 2023 Q4 |  |  |  | Digicampus, Humanity Hub, The Hague
alkemio | Epic,Roadmap Candidate | Usage of Alkemio platform identities for Matrix | Elaborated | Functionality: Strategic | 80 | 2023 Q3
alkemio | Epic,Roadmap Discussion | My home page with activity | Current / next quarter |  | 80 | 2023 Q3
alkemio | Epic,UX,A: Platform | Innovation Hubs: Specified Hubs, Hub visibility | Done | Functionality: Strategic | 50 | 2023 Q2 | 2023-05-09 | 10 |  | UWV
alkemio | Epic | Documents: Secure storage with management | Done | Functionality: Tactical | 50 | 2023 Q2 | 2023-05-09 |  |  | TNO
alkemio | Epic | Innovation Library for users | Done |  | 30 | 2023 Q2 | 2023-05-09
alkemio | Epic,UX,A: Context | Structure refresh Challenge + Opportunity level | New | Functionality: Strategic | 50 | 2023 Q2
alkemio | Epic,Roadmap Discussion | New Space language preferences | New
alkemio | Epic,Roadmap Discussion | Activity tracking: deletion, additional entry types | New |  |  | 2023 Q3
alkemio | Epic,Roadmap Discussion | Refresh preferences for notifications | New |  |  | 2023 Q3 |  |  | Denise Larsson
alkemio | Epic,Roadmap Candidate | Insights on platform usage | New |  |  | 2023 Q3
alkemio | Epic | Generative AI first use case | New |  |  | 2023 Q3