## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date: | 2023-02-28
Current Sprint: | 56
Time Period | Time Period End | Features allocation, % | Development Sprints available | Points / sprint | Capacity | Comments
2023 Q1 | 2023-03-28 | 80% | 2 | 200 | 320
2023 Q2 | 2023-06-30 | 70% | 6.5 | 200 | 910
2023 Q3 | 2023-09-30 | 50% | 6.5 | 200 | 650
2023 Q4 | 2023-12-31 | 50% | 7 | 200 | 700
2024 | 2024-12-31 | 50% | 26.5 | 200 | 2650
Formulas:
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM(B3,1))/2
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM([Time Period End, row above],1))/2

## Capacity
Delivery | Planned | Available | Functionality: Tactical | Maintenance | Operations: Security | Operations: Effectiveness | Usability | Performance | Functionality: Strategic | Not specified
2023 Q1 | 400 | 320 | 0 | 30 | 20 | 20 | 40 | 50 | 210 | 30
2023 Q2 | 930 | 910 | 190 | 80 | 0 | 140 | 120 | 0 | 390 | 10
2023 Q3 | 1080 | 650 | 160 | 0 | 150 | 100 | 310 | 90 | 270 | 0
2023 Q4 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GITHUB_EPICS
Assignees | Repository | Labels | Title | Status | Period | Partner | Sprint | EpicPoints | SprintPoints | Type | Milestone | Release
Valentin Yanakiev | alkemio | Epic,UX,client | Search++: Within a Hub, Contributions, UI | Done | 2023 Q1 | UWV, VNG | 2023-02-14 | 30 | 20 | Functionality: Tactical
Andrew Pazniak | alkemio | Epic,UX | Landing page v1 | Done | 2023 Q1 |  | 2023-02-14 | 50 | 20 | Functionality: Strategic
Aleksandar Stojanovic | alkemio | Epic | User to user communication via notifications | Done | 2023 Q1 | UWV | 2023-02-14 | 80 | 10 | Functionality: Tactical
Carlos Cano | alkemio | Epic | Calendar Events V2 | Done | 2023 Q1 | UWV | 2023-02-14 | 30 | 20 | Functionality: Tactical |  | Release 230208
| alkemio | Epic,UX | Grouping of Hubs by theme | Done | 2023 Q1 |  | 2023-02-14 | 20 | 10 | Functionality: Strategic
| alkemio | Epic | Calendar Events per community | Done | 2023 Q1 | UWV | 2023-01-31 | 50 |  | Functionality: Tactical |  | Release 230208
| alkemio | Epic | Capacity Planning | Done | 2023 Q1 |  | 2023-01-31 | 10 | 10 | Maintenance
Svetoslav Petkov | alkemio | Epic | Reporting: Northstar Metric | Done | 2023 Q1 |  | 2023-01-31 | 50 | 30 | Functionality: Strategic | Core Capabilities
| alkemio | Epic | UX Refinements: Round 2 | Done | 2023 Q1 |  | 2023-01-17 | 30 | 30 | Functionality: Tactical
| alkemio | Epic | UX Refinements - Round 3 | Defined | 2023 Q1 |  | 2023-02-28 | 20 | 30 | Usability
Rene Honig,Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Security: Authentication via Microsoft identities - basic | Defined | 2023 Q1 |  | 2023-02-28 | 20 | 20 | Operations: Security
| alkemio | Epic,UX | Journey Pages structure roadmap | Being elaborated | 2023 Q2 |  |  | 50 |  | Functionality: Strategic
Valentin Yanakiev | alkemio | Epic,Infrastructure | Custom URL for Demo Hubs on production | Being elaborated | 2023 Q1 |  | 2023-02-28 | 80 | 30 | Functionality: Strategic
| alkemio | Epic,UX | Innovation Spaces: Specified Communities + visuals | Being defined | 2023 Q1 | UWV | 2023-03-14 | 80 | 10 | Functionality: Strategic
Svetoslav Petkov | alkemio | Epic | Community forum on the platform | Defined | 2023 Q1 |  | 2023-02-28 | 20 | 10 | Functionality: Strategic
Valentin Yanakiev | server | Epic,server | Domain Model: Profiles | Defined | 2023 Q1 |  | 2023-02-14 | 30 | 20 | Maintenance
| alkemio | Epic,UX | UX Refinements - Round 4 | Being elaborated | 2023 Q2 |  |  | 30 |  | Usability
Andrew Pazniak | alkemio | Epic,UX | Contributor visibility | Defined | 2023 Q3 |  |  | 30 |  | Functionality: Tactical
| alkemio | Epic,UX | Hub visibility for unauthorized users | Elaborated | 2023 Q2 |  |  | 10 |  | Usability
Valentin Yanakiev | alkemio | Epic | Release mgmt: Documentation, process + split | Being elaborated | 2023 Q2 |  |  | 50 |  | Operations: Effectiveness
| alkemio | Epic,UX,Roadmap Candidate | Email Templates | Being elaborated |  |  | 2023-03-14
| alkemio | Epic,Roadmap Candidate | Improved content editing | Being elaborated
| alkemio | Epic | Whiteboard: interactive multi-user editing | Being elaborated | 2023 Q2 |  |  | 80 | 20 | Functionality: Strategic
| alkemio | Epic,UX | Contribute Page | Icebox | 2023 Q3 |  |  | 30 |  | Usability
Svetoslav Petkov | alkemio | Epic | Smart search v1 | Icebox | 2023 Q3 | UWV |  | 80 |  | Functionality: Strategic
Valentin Yanakiev | alkemio | Epic | Release mgmt: release notes + changelog | Icebox | 2023 Q3 |  |  | 30 |  | Operations: Effectiveness
Svetoslav Petkov | alkemio | Epic | Reporting: Platform usage insights | Icebox | 2023 Q3 |  |  | 20 |  | Operations: Effectiveness
| alkemio | Epic | Choral Explanations | Icebox | 2023 Q3 | TIP |  |  |  | Functionality: Strategic
| alkemio | Epic | Sharing: social media | Icebox | 2023 Q3 |  |  | 20 |  | Usability
| alkemio | Epic,UX,Roadmap Candidate | Hide / turn functionalities off | Icebox
| alkemio | Epic | Integration of other online tools | Icebox
| server | Epic,server | Server: Performance Optimization | Icebox | 2023 Q3 |  |  | 30 |  | Performance
| alkemio | Epic,UX | Callouts: Sorting control | Icebox | 2023 Q3 |  |  | 20 |  | Usability
| alkemio | Epic,QA | Performance + scalability testing | Icebox | 2023 Q3 |  |  | 30 |  | Performance
| alkemio | Epic | Preference for aggregated of notifications | Icebox | 2023 Q3 |  |  | 80 |  | Usability
| alkemio | Epic | Follow a Hub / Challenge / Opportunity | Icebox | 2023 Q3 |  |  | 50 |  | Usability
| client-web | epic,client,UX | Knowledge Management in journeys | Icebox | 2023 Q3 |  |  | 30 |  | Functionality: Tactical
| alkemio | Epic | Innovation library usage | Icebox | 2023 Q3 |  |  | 30 |  | Functionality: Strategic
| alkemio | Epic | Search results validated in service | Icebox | 2023 Q3 |  |  | 30 |  | Performance
Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Operational security analysis | Icebox | 2023 Q3 |  |  | 20 |  | Operations: Security
Valentin Yanakiev | infrastructure-operations | security,Epic | Security: Secret management | Icebox | 2023 Q3 |  |  | 20 |  | Operations: Security
| alkemio |  | Image upload in content editor | Icebox |  |  |  | 30 |  | Functionality: Tactical
Carlos Cano | alkemio | Epic | Visuals on Journeys: Enhanced selection + suggested imageswith alternative text | Icebox | 2023 Q3 | Envision |  | 30 |  | Usability
| alkemio | Epic | Ecosystem Analytics: prototype | Icebox | 2023 Q3 |  |  | 80 |  | Functionality: Strategic
| alkemio | Epic,UX | Hub Visualization component | Icebox | 2023 Q3 |  |  | 30 |  | Functionality: Strategic
Svetoslav Petkov | alkemio | Epic,UX | Library: Innovation Pack management | Icebox | 2023 Q3 |  |  | 50 |  | Functionality: Strategic
Denise Larsson | alkemio | Epic,UX | Invitations to Hub | Icebox | 2023 Q3 |  |  | 50 |  | Functionality: Tactical
| alkemio | Epic | Keyboard navigation | Icebox | 2023 Q3 |  |  | 50 |  | Usability
| alkemio | Epic | Performance: Dataloaders / field resolvers | Being elaborated | 2023 Q1 |  | 2023-02-28 | 50 | 30 | Performance
| alkemio | Epic,Roadmap Candidate | UX Refinements Round 5 | Current / next quarter
| alkemio | Epic,UX | Comments: Improved interaction | Current / next quarter | 2023 Q2 |  |  | 30 |  | Functionality: Tactical
Rene Honig,Valentin Yanakiev | alkemio | Epic | Security: Kubernetes hardening | Icebox | 2023 Q3 |  |  | 50 |  | Operations: Security
| alkemio | Epic | Security: Control of provider per organization | Icebox | 2023 Q3 |  |  | 50 |  | Functionality: Tactical
Valentin Yanakiev | alkemio | Epic | Infrastructure: Maintainability | Icebox | 2023 Q3 |  |  | 50 |  | Operations: Effectiveness
| alkemio | Epic | Login Refinements / Kratos | Icebox | 2023 Q3 |  |  | 30 |  | Operations: Security
Rene Honig,Valentin Yanakiev | hub | Epic,operations | Security: Client code execution / injection | Icebox | 2023 Q3 |  |  | 30 |  | Operations: Security
| alkemio | Epic,UX | Callouts in context | Current / next quarter | 2023 Q2 | UWV |  | 30 |  | Functionality: Strategic
Valentin Yanakiev | alkemio | Epic | Data Integrity: v2 | Current / next quarter | 2023 Q2 |  |  | 30 |  | Operations: Effectiveness
| alkemio | Epic,UX | Whiteboard: Usability v1 | Current / next quarter | 2023 Q2 |  |  | 30 |  | Functionality: Tactical
Valentin Yanakiev | alkemio | Epic | Operations: Platform monitoring | Current / next quarter | 2023 Q2 |  |  | 30 |  | Operations: Effectiveness
Svetoslav Petkov | alkemio | Epic | Handling of Time | Current / next quarter | 2023 Q2 |  |  | 30 | 10 | Usability
Valentin Yanakiev | alkemio | Epic | Domain model: Naming alignment | Current / next quarter | 2023 Q2 |  |  | 30 |  | Maintenance
| alkemio | Epic,UX,client | Update of Journey settings tab | Current / next quarter | 2023 Q2 |  |  | 20 |  | Usability
| alkemio | Epic | Documents: Wider usage, Management and limits | Current / next quarter | 2023 Q2 |  |  | 50 |  | Functionality: Strategic
| alkemio | Epic | Documents: Storage with privacy | Current / next quarter | 2023 Q2 |  |  | 50 |  | Functionality: Tactical
| alkemio | Epic | Demo environment data migration + retirement | Current / next quarter | 2023 Q2 |  |  | 10 |  | Operations: Effectiveness
| alkemio | Epic,Security | Security headers hardening | Current / next quarter | 2023 Q2 |  |  | 10
| alkemio | Epic | Innovation spaces: readiness for release | Current / next quarter | 2023 Q2 |  |  | 50 |  | Functionality: Strategic
| alkemio | Epic | User to user messaging via message box | Current / next quarter | 2023 Q2 |  |  | 50 |  | Functionality: Tactical
| alkemio | Epic | Community Terms + Conditions | Current / next quarter | 2023 Q2 |  |  | 80 |  | Functionality: Strategic
Svetoslav Petkov | alkemio | Epic,UX | Branding at platform level | Current / next quarter | 2023 Q2 |  |  | 30 |  | Functionality: Strategic
| alkemio | Epic | Accessibility Gap Analysis | Current / next quarter | 2023 Q2 |  |  | 30 |  | Usability
| alkemio | Epic,A: Community | Engagement: user newsletter signup during registration | Current / next quarter | 2023 Q2 |  |  | 20 |  | Functionality: Strategic
Valentin Yanakiev | alkemio | Epic | Operations: Kratos, Cluster Health | Current / next quarter | 2023 Q2 |  |  | 20 |  | Operations: Effectiveness
| alkemio | Epic | Matrix adapter as a separate service | Done | 2023 Q1 |  | 2023-01-17 | 50 | 40 | Maintenance
Neil Smyth | alkemio | Epic | Private challenges | Done | 2023 Q1 |  | 2023-01-31 | 50 | 30
Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Kratos 0.11 Update | Done | 2023 Q1 |  | 2023-01-17 | 50 |  | Operations: Security
Aleksandar Stojanovic | alkemio | Epic | Callout: single canvas type | Done | 2023 Q1 |  | 2023-01-17 | 30
| alkemio | Epic | Data Integrity | Done | 2023 Q1 |  | 2023-01-17 | 50 |  | Maintenance
| alkemio | Epic | QA Test suites catchup | In progress | 2023 Q2 |  | 2023-02-14 | 50 | 20 | Maintenance
| alkemio | Epic | Notifications dashboard | New | 2023 Q2 |  |  | 30 |  | Functionality: Tactical
Valentin Yanakiev | alkemio | Epic,Roadmap Candidate | Error Handling: Presentation improvements | New | 2023 Q3 |  |  | 30 |  | Usability
| alkemio | Epic,UX | Search in Contribute page | Being elaborated | 2023 Q1 | UWV | 2023-03-14 | 20
| alkemio | Epic | Reporting: Sharing of analysis | Being elaborated | 2023 Q1 |  | 2023-03-14 | 20 |  | Operations: Effectiveness
| alkemio | Epic,UX | Community tab in Hub menu | Being elaborated | 2023 Q1 |  | 2023-03-14 | 20 |  | Usability
| alkemio | Epic,UX | Community Application Questions | Being elaborated | 2023 Q1 |  | 2023-02-28 | 10
| homepage | UX,Epic | Landing page: refinements + maintainability | Being elaborated | 2023 Q1 |  | 2023-02-28 | 30 |  | Functionality: Strategic
| client-web | epic,client,Roadmap Candidate | Client: Developer documentation, roadmap | New
| alkemio | Epic,Roadmap Candidate | Search: Additional contiribution types | New