## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Time Period | Time Period Start | Time Period End | Features allocation, % | Development Sprints available | Vacations / Done (sprints) | Available Sprints | Points / sprint | Capacity | Comments
2023 Q1 | 44928 | 45012 | 0.8 | 6 | 6 | 0 | 200 | 0
2023 Q2 | 45012 | 45096 | 0.8 | 6 | 6 | 0 | 200 | 0 |  | Note: update to have each period start / end adjustable
2023 Q3 | 45096 | 45194 | 0.6 | 7 | 5.5 | 1.5 | 200 | 180
2023 Q4 | 45194 | 45292 | 0.5 | 7 | 0.5 | 6.5 | 200 | 650
2024 Q1 | 45292 | 45383 | 0.5 | 6.5 | 0.5 | 6 | 200 | 600
2024 Q2 | 45383 | 45474 | 0.5 | 6.5 | 0.5 | 6 | 200 | 600
2024 H2 | 45474 | 45657 | 0.5 | 13.0714 |  | 13.0714 | 200 | 1307.1429

## Capacity
Delivery | Planned | Available | Done | Total | Functionality: Tactical | Maintenance | Operations: Security | Operations: Effectiveness | Usability | Performance | Functionality: Strategic | Not specified
2023 Q1 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2023 Q2 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2023 Q3 | 0 | 180 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2023 Q4 | 0 | 650 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2024 Q1 | 0 | 600 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2024 Q2 | 0 | 600 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
2024 H2 | 0 | 1307.1429 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!

## GITHUB_EPICS
Assignees | Repository | Labels | Title | Status | Sprint | Milestone | Period | EpicPoints | Partner | SprintPoints | Milestone
| alkemio | Epic | Client Tech debt: Q4 2025 | Being defined
| alkemio | Epic | Working on Alkemio as an Organization | Being defined | 2025-10-28
Evgeni Dimitrov | alkemio | Epic,QA | QA: Test Suites extensions Q4 | Being defined |  | Improved Confidence in the Platform | 2024 Q3
| alkemio | Epic | Whiteboards: Robustness + performance Q4 | Being defined |  | Improved Confidence in the Platform
| alkemio | Epic,QA,Product Discussion,Rhea Team | QA on multi-user collaboration on whiteboard | Being defined | 2025-10-28 | Improved Confidence in the Platform | 2024 Q2 |  |  | 13
Svetoslav Petkov,user | alkemio | Epic | Reporting: (automated) sharing of reports , read only access | Being defined |  |  | 2024 Q2 | 20
| alkemio | Epic,Roadmap Candidate | Client component library in Figma | Being defined |  |  | 2024 Q2 |  |  | 8
| alkemio | Epic | Simpler URLs | Being defined |  | Spaces with Subspaces | 2024 Q3
Valentin Yanakiev | alkemio | Epic,Infrastructure | Storage management | Being defined | 2025-10-28 |  | 2024 Q3
| alkemio | Initiative | I: Analytics via connectivity graph v1 | Being defined
| alkemio | Initiative | I: Maintainability | Being defined
| alkemio | Initiative | I: Journey structure refresh | Being defined | 2023-03-14
| alkemio | Initiative | Innovation library - Agreements | Being defined
| alkemio | Initiative | I: Onboarding the community | Being defined
| alkemio | Initiative | I: Innovation Hubs | Being defined
| alkemio | Initiative | I: Platform responsiveness | Being defined
| alkemio | Initiative | I: Guidance for users | Being defined
| alkemio | Initiative | I: Platform Management | Being defined
| alkemio | Initiative | I: Accessibility | Being defined
| alkemio | Initiative | I: Content + Knowledge Management | Being defined
| alkemio | Initiative | I: Notifications | Being defined
| alkemio | Initiative | I: Library population, usage + feedback | Being defined
| alkemio | Initiative | Content on the platform | Being defined
| alkemio | Initiative | I: Innovation Library | Being defined
| alkemio | Initiative | I: Enriched User Profiles | Being defined
| alkemio | Initiative | I: Smart search | Being defined
| alkemio | Initiative | I: RT Whiteboard | Being defined
| alkemio | Epic | Bucket: Enhancing UX: Visual improvements | Being defined
Bobby Kolev | alkemio | Epic | Video calling services | Being elaborated | 2025-09-16
Bobby Kolev,Svetoslav Petkov | alkemio | Epic | Notifications: Controls per space | Being elaborated | 2025-10-14 | Notifications: on the platform, per space | 2024 Q2
| alkemio | Epic | Notifications: Grouping + additional types | Being elaborated | 2025-10-28 | Notifications: on the platform, per space | 2024 Q2 | 50
Polina Boneva | alkemio | Epic,client | Accessibility: WCAG 2.1 | Being elaborated | 2025-09-30
| alkemio | Epic | Templates: Interaction Space library and platform library | Being elaborated | 2025-09-16 | Templates: Complete set | 2024 Q2 | 30
Valentin Yanakiev | alkemio | Epic | Sharing/Collaborating in callouts with unauthenticated users | Being elaborated | 2025-09-16
Valentin Yanakiev | alkemio | Epic,Atlas Team,Rhea Team | Independent issues | Being elaborated | 2025-09-16
| alkemio | Epic | Calendar events Bucket: Importing/Exporting; flexible time; show events from related sub/space | Being elaborated | 2025-10-14 |  | 2024 Q3
| infrastructure-operations | operations,Epic,Infrastructure | External Penetration Testing [Q4 2025] | Being elaborated | 2025-10-14 |  |  |  | Avans
| alkemio | Epic | Subscriptions on all Space pages | Being elaborated | 2025-10-28
| alkemio | Epic,Roadmap Discussion,New this Sprint | Licensing: Account management | Being elaborated | 2025-10-14 | Products + Licensing
| alkemio | Epic | Flexible & Templatable community roles | Being elaborated |  | Innovation Professional Support | 2024 Q2 | 30
| alkemio | Epic | VC: Single user interaction | Being elaborated
| alkemio | Epic,Product Team | Space layout | Being elaborated | 2025-10-28
Valentin Yanakiev | alkemio | Epic | Infrastructure: Maintainability | Being elaborated |  | Improved Confidence in the Platform | 2024 Q2 | 30
| alkemio | Epic | Authorization Checking Service; cleanup | Being elaborated |  |  | 2024 Q2
| alkemio | Epic,Product Discussion | Private sub-subspace | Being elaborated |  | Spaces with Subspaces | 2024 Q2 | 20
| alkemio | Epic,Roadmap Discussion | Refresh Contributors page | Being elaborated |  |  | 2024 Q2 | 20
| alkemio | Epic,Roadmap Discussion | Bucket: Content editing improvements | Being elaborated |  |  | 2024 Q2 | 20
| alkemio | Epic | Activity tracking: deletion | Being elaborated |  |  | 2024 Q2 | 30
| alkemio | Epic,Roadmap Discussion | InnovationFlow: Creation + management | Being elaborated |  |  | 2024 Q2 | 80
| alkemio | Epic | Using Temporary Storage | Being elaborated
| alkemio | Epic | Enhance Tag Management and Usability | Being elaborated
| alkemio | Epic | Bucket: User Documentation | Being elaborated
Simone | alkemio | Epic,Rhea Team | Fixing MD editor bugs | Defined | 2025-10-28
| alkemio | Epic | VCs: Monitoring + operations | Defined |  | Virtual Contributors: Q3 2024 | 2024 Q3
| alkemio | Epic,Product Team | Memberships: consistency, organization | Defined |  | Create your own Space: GA
| alkemio | Epic | Authentication: Identity Management | Defined |  | Create your own Space: GA | 2024 Q3
Valentin Yanakiev,Svetoslav Petkov | alkemio | Epic | API usage performance / monitoring / audit trail | Defined |  | Improved Confidence in the Platform | 2024 Q3
| alkemio | Epic | Platform Administration | Defined
| alkemio | Epic,Roadmap Discussion,Product Discussion | Journey settings: challenge, community membership policy | Defined |  |  | 2024 Q2 | 20
| alkemio | Epic,Atlas Team | Licensing: Runtime enforcement | Defined |  | Create your own Space: GA | 2024 Q3
| alkemio | Epic,QA | QA: Test suite user authentication flows | Defined |  |  | 2024 Q2 | 30
| alkemio | Epic,Atlas Team | VC: Expert engine space data retrieval + loading | Elaborated |  | Virtual Contributors: Q3 2024 | 2024 Q3
| alkemio | Epic | Forum: ready for release notes | Elaborated |  |  | 2024 Q2
| alkemio | Epic | Bucket: Server performance | Icebox
| alkemio | Epic | Welcome dialog for new members of a Journey | Icebox
| alkemio | Epic | Bucket: Enhancing UX: Reducing Clicks and Scrolling | Icebox
| alkemio | Epic | Bucket: Enhancing UX: Guidance in current functionality | Icebox
| alkemio | Epic | Bucket: Forum improvements | Icebox
| alkemio | Epic | Bucket: Enhancing UX: Streamlining User Interaction with Existing Functionality | Icebox
| alkemio | Epic,Product Team,client | UX: Sorting control on the client | Icebox
| alkemio | Epic | Bucket: Journey membership UX improvements | Icebox
| alkemio | Epic | Bucket: User login / membership improvements | Icebox
| infrastructure-operations | operations,Epic,Infrastructure | Reporting: geolocation, sign ups | Icebox
| alkemio | Epic | Knowledge: Suggested best practice templates | Icebox
| alkemio | Epic,Product Discussion | Activity: Auditing for admins | Icebox
| alkemio | Epic,Product Discussion | Bucket: Guidance: Improvements | Icebox |  |  | 2024 Q2
| alkemio | Epic | Choral Explanations | Icebox |  | Callouts: additional contribution types | 2024 Q3 |  | TIP
| alkemio | Epic | Sharing metrics of Space activity with leads | Icebox |  |  | 2024 Q3
| alkemio | Epic,Product Discussion | Multiple Language Support | Icebox |  | Collaboration templates | 2024 Q2
| alkemio | Epic,Product Team,Product Discussion | Innovation Flow: Definition to include goal/checklist/callouts | Icebox |  |  | 2024 Q3 | 80
| alkemio | Epic | Integration of other online tools | Icebox |  |  | 2024 Q3
| alkemio | Epic | Sharing: social media | Icebox |  |  | 2024 Q3 | 20
| alkemio | Epic,Product Team,Product Discussion | Search in Contribute page | Icebox |  | Search: Smart | 2024 Q3 | 20
Valentin Yanakiev | infrastructure-operations | operations,Epic,Infrastructure | Operational security analysis | Icebox |  |  | 2024 Q3 | 20
| alkemio | Epic | Visuals on Journeys: Enhanced selection + suggested images | Icebox |  |  | 2024 Q3 | 30
| alkemio | Epic,Product Team | Hide / turn functionalities off | Icebox |  |  | 2024 Q3
| alkemio | Epic,QA | QA: Test suites expanded | Icebox
| test-suites | Epic,QA | Vulnerability scanning | Icebox
| alkemio | Epic | Governance: Security Audit + fixes | Icebox
| alkemio | Epic,Roadmap Candidate | Database: Robust deletions | Icebox
| alkemio | Epic | Bucket: Innovation flows | Icebox
Valentin Yanakiev,Donna | alkemio | Epic,Product Discussion | Authentication: Support for public sector identities | In progress | 2025-09-16 | Improved Confidence in the Platform
Vladimir Aleksiev | alkemio | Epic | VC: Enable prototyping | In progress | 2025-09-16
Bobby Kolev | alkemio | Epic | Notifications: InApp full set of events | In progress | 2025-09-16 | Notifications: on the platform, per space
| alkemio | Epic | Incident Response Protocol and Improvements | In progress | 2025-10-14
| alkemio | Epic | Infrastructure: Maintainability Q2 2025 | In progress
| alkemio | Epic,Atlas Team | Server: robustness + performance Q2 2025 | In progress |  | Improved Confidence in the Platform
Valentin Yanakiev | alkemio | Epic | Release mgmt: Process + tooling | In progress |  | Improved Confidence in the Platform | 2024 Q2 | 50
Carlos Cano | alkemio | Epic | Callouts: updated UI/UX | New | 2025-09-16
Bobby Kolev | alkemio | Epic | Template pack: UI improvements | New | 2025-09-16
Bobby Kolev | alkemio | Epic | Extend set of events for notifications (inapp + email) | New | 2025-09-16
| alkemio | Epic | Innovation Flow: settings and default callout content | New | 2025-09-30 | [5 empty] | Core Capabilities
| alkemio | Epic | Converter service: Picture to whiteboard | New | 2025-09-16
Svetoslav Petkov | alkemio | Epic | [Bucket] Reducing errors & warnings | New | 2025-09-16
| alkemio | Epic | (Sub)Space Templates: Preview + Management | New | 2025-10-14
| alkemio | Epic | End-end tracking across welcome site > platform | New | 2025-10-28
| infrastructure-operations | operations,QA | Stress testing the platform | New | 2025-10-28
| alkemio | Epic,Product Discussion | User-user messaging (Matrix) | New | 2025-10-28 | User to user messaging on the platform
| alkemio | Epic | Matrix scalability | New | 2025-10-28
| alkemio | Epic,Roadmap Discussion | Scalable whiteboard collaboration service | New | 2025-10-28
| alkemio | Epic,QA,Refinement,Atlas Team | Test suites: validate database content | New | 2025-10-28 | Improved Confidence in the Platform
Neil Smyth | alkemio | Epic,client,Product Discussion | Visible Errors to the user - Improve observability and feedback | New | 2025-10-14
| alkemio | Epic | Hidden Spaces | New | 2025-10-28
| alkemio | Epic,Product Discussion | Command line utilities for non-devs | New | 2025-10-28
| alkemio | Epic | VCs: Data freshness | New |  | Virtual Contributors: Q3 2024
Maloe | product | Epic,Product Team | Epic: Engaging Platform Library | New
| alkemio | Epic | VC: Service AI - community what has happened | New
| alkemio | Epic | Bucket: VC improved functionality | New |  | Virtual Contributors: Q3 2024
| alkemio | Epic | VC: Image generation | New |  | Virtual Contributors: Q3 2024
| alkemio | Epic | VC: Controls on data sources | New |  | Virtual Contributors: Q3 2024
| infrastructure-operations | operations,Epic,Infrastructure | Encryption at rest | New | 2025-10-28
| alkemio | Epic | Client: time to first load | New | 2025-10-28
| alkemio | Epic,Product Team | Transforming static contributors/subspaces blocks into callouts | New
| alkemio | Epic | Account management for Start pages | New
| alkemio | Epic,QA,Product Discussion | Test suite: VCs | New | 2025-10-28
| alkemio | Epic,Atlas Team | VC: Embeddings management | New
| alkemio | Epic | VC: AI Server split from server | New |  | Virtual Contributors: Q3 2024
| alkemio | Epic | VCs: Multiple context types | New |  | Virtual Contributors: Q3 2024
Carlos Cano,Neil Smyth | alkemio | Epic,Rhea Team | Inviting an organization into a Space | New |  | Improved Confidence in the Platform
Bobby Kolev,Donna | alkemio | Epic | Monitoring: Q4 errors investigation | New | 2025-10-28 | Improved Confidence in the Platform
| alkemio | Epic,Roadmap Discussion | Moving between levels: pro/de-moting (Sub)Spaces, moving callouts | New | 2025-10-28
| alkemio | Epic,Product Team,Roadmap Discussion | Account: Consistent settings per resource | New |  | Improved Confidence in the Platform
| alkemio | Epic,Roadmap Discussion | AI: Automated scope analysis for risk-based testing | New
| alkemio | Epic,Product Team,Roadmap Discussion | Visibility: clean, clear, and consistent | New
Valentin Yanakiev | alkemio | Epic,QA | QA Management Tooling + Plan | New |  | Improved Confidence in the Platform
| alkemio | Epic | Licensing: Entitlement usage inside Spaces | New | 2025-10-28 | Products + Licensing
| alkemio | Epic | Reporting: User flows | New |  | Usage insights
| alkemio | Epic,Roadmap Discussion | Resource controls: demo, searchability, hidden etc | New |  | Create your own Space: GA
| alkemio | Epic,Product Discussion | Whiteboard: history | New
| alkemio | Epic,Roadmap Discussion,Product Discussion | Organizations: Flexibility/Less formal + Simplify Unverified profiles | New |  | Organization profile: Clear & fit for purpose
| alkemio | Epic | Account Mgmt v2: bucket (orgs, verification. ...) | New |  | Create your own Space: GA
| alkemio | Epic | Inviting people for platform role | New |  | User Engagement with the platform
| alkemio | Epic | Reporting: access, other features requiring license | New
| alkemio | Epic,Product Discussion | Specify the email sender for community notification emails | New |  | Smoothly joining a community
| alkemio | Epic,Product Team | Membership models | New
| alkemio | Epic | Release mgmt: optimization | New
| alkemio | Epic,client | Compliance: Tracking + cookie handling on client | New
| alkemio | Epic | Data integrity v3 | New
| alkemio | Epic,client | Search: smart tags | New |  | Search: Smart
| alkemio | Epic | Subscriptions: Payments infrastructure | New |  | Products + Licensing
| alkemio | Epic | Bucket: Engaging User Profiles / Profiles per community | New
| alkemio | Epic | Whiteboards to generate content | New |  | Whiteboard to generate content
| alkemio | Epic | Linking contributions | New |  | Connectivity Graph
| alkemio | Epic | Test Suites Tech Debt | New
| alkemio | Epic | Domain model: refinements | New
| alkemio | Epic | Static Code analysis: replacement for BCH | New
| alkemio | Epic,client | QA: Client Test Suites setup | New
| alkemio | Epic,server | Server: Code clean up / optimization | New
Neil Smyth | alkemio | Epic | Domain: ActorGroups ==> Actors with Tags | New
| alkemio | Epic | Dev Tooling: Migrate to Yarn | New
| alkemio | Epic | api: roadmap + design | New
| alkemio | Epic | api: enhanced documentation | New
Neil Smyth | infrastructure-operations | operations,Epic,Infrastructure | Reporting: configuration management + deployment | New
| alkemio | Epic | Emails associated with a user | New
| alkemio | Epic | LinkedIn: connected accounts + usage for populating Alkemio profiles + messages | New
| alkemio | Epic,Product Discussion | Organizations: Signed up versus profiles | New
| alkemio | Epic | Platform visibility Collaboration professionals | New
| alkemio | Epic | Simple versions of Alkemio | New
| infrastructure-operations | operations,Epic,Infrastructure | Acc environment on demand | New
| server | Epic,user story,server | ORM Mapping Layer optimisation | New
| test-suites | Epic,QA | QA: Test Suites maintainability | New
| test-suites | Epic,QA | Subscriptions: Test framework + initial limited test suite | New
Evgeni Dimitrov | test-suites | Epic,QA | QA: Expand set of server API E2E tests | New
| server | Epic,user story,server | Caching at the cluster level | New
Evgeni Dimitrov | test-suites | Epic,QA | Search UI Tests | New
| test-suites | Epic,QA | System test plan tracking | New
| notifications | Epic | Notifications: configuration management flexibility | New
| alkemio | Epic | Chat Guidance: Multiple sessions | New
| alkemio | Epic,Product Discussion | Upgrading/Downgrading Space license | New |  | Products + Licensing
| alkemio | Epic | Transparency on Space settings/library/etc for Space members | New |  | Smoothly joining a community
| alkemio | Epic,Product Team | Policy Updates | New | 2024-06-18 |  | 2024 Q2
| alkemio | Epic | Invitations / applications: polishing | New |  | Smoothly joining a community
| alkemio | Epic | User verification flow | New |  | Create your own Space: GA
| alkemio | Epic | Cluster Health Monitoring Dashboards | New
| alkemio | Epic | Bucket: VC improving the answers/response | New
| alkemio | Epic | Stability: Client error tracing + reproduction | New
| alkemio | Epic,QA,Product Discussion | Performance Test Suite for api | New
| alkemio | Epic | Act as... | New |  | Innovation Professional Support
| alkemio | Epic | Bucket: Open Source Integrations | New
| alkemio | Epic | Consistency in notifications for interaction in a space | New
| alkemio | Epic | Onboarding new Space members - after sign-up flow | New
| alkemio | Epic,Product Discussion | VS: Meta information on knowledge base | New
| alkemio | Epic,Roadmap Discussion | Reporting: additional details | New |  | Usage insights
| alkemio | Epic | Client Optimization: Optimizing Assets: images | New | 2025-10-28
| alkemio | Epic | Client Optimization: Optimizing Assets: Serve static files/CDN | New
| alkemio | Epic | Client Optimization: Optimizing code execution | New
| alkemio | Epic | Client Optimization: Server Calls | New
| alkemio | Epic,A: Community | Open Badges support | New
| alkemio | Epic,Roadmap Discussion,Product Discussion | Space language | New
| alkemio | Epic,Roadmap Discussion,Product Discussion | Polis | New
| alkemio | Epic,Roadmap Discussion | Privacy/GDPR: user control on visibility | New | 2025-10-28
| alkemio | Epic,Product Team | Dutch website + documentation | New
| alkemio | Epic,Product Discussion | Transfer of Callouts between spaces | New
| alkemio | Epic,Product Discussion | Inviting users to organization | New
| alkemio | Epic | 3rd party upgrade Q1+2 2025 | New
| alkemio | Epic,Atlas Team,Rhea Team | Notifications: Bucket tidy up | New |  | Notifications: on the platform, per space
| alkemio | Epic | VC: Work product output | New
| alkemio | Epic | VC: Workproduct input | New
| alkemio | Epic | Onboarding flow: polishing | New
| alkemio | Epic | Butcket: UX around a release | New
| alkemio | Epic,Product Discussion | New Callout Types | New
| alkemio | Epic | Bucket: OS/Browser version issues (to keep track) | New
| alkemio | Epic | Matrix: Interaction with rooms outside directly | New
| alkemio | Epic,Product Discussion | Infrastructure Cost optimization | New | 2025-10-14
| alkemio | Epic | Memo: Commenting & other Refinements | New
| alkemio | Epic | Basic usage supported on mobile | New | 2025-10-14
| alkemio | Epic | Multiple email support | Roadmap |  |  | 2024 Q3
| alkemio | Epic | Follow a Space / Challenge / Opportunity | Roadmap |  |  | 2024 Q2 | 50
| alkemio | Epic | Preference for aggregated of notifications | Roadmap |  |  | 2024 Q3 | 80
| alkemio | Epic | Notifications: Aggregation of events | Roadmap
| alkemio | Epic | Exposing Matrix Externally (Usage of Alkemio platform identities for Matrix) | Roadmap | 2025-10-28 |  | 2024 Q2 | 80
Valentin Yanakiev,Svetoslav Petkov | alkemio | Epic | Reporting: Active usage monitoring | Roadmap |  | Usage insights
| alkemio | Epic | Licensing: Visibility on account + enforcement on resource creation | Roadmap |  | Products + Licensing
| alkemio | Epic | Welcome site v3 | Roadmap |  | Products + Licensing | 2024 Q2
Valentin Yanakiev | alkemio | Epic | Release mgmt: release notes + changelog | Roadmap |  |  | 2024 Q3 | 30
| alkemio | Epic | Bucket: Whiteboards | Roadmap |  |  | 2024 Q2
| alkemio | Epic,Roadmap Discussion,Product Discussion | Activity Tracking: refresh of contributions monitoring | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic,Roadmap Discussion | Enhanced Sign up flow | Roadmap |  |  | 2024 Q3
| alkemio | Epic | Homepage / Dashboard: Private workspace | Roadmap |  |  | 2024 Q2
Valentin Yanakiev | alkemio | Epic | Storage: Improved handling of documents that are uploaded | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic | Managing the user-organization + org roles relationship | Roadmap |  |  | 2024 Q2 | 50
| alkemio | Epic | Config mgmt: Helm deployments for k8s | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic,client,Product Discussion | Search: Add forum, and help content to the search results | Roadmap |  | Search: Smart | 2024 Q2 | 50
| alkemio | Epic,server,Security | Development versions refresh | Roadmap |  |  | 2024 Q2
| alkemio | Epic,Roadmap Discussion,Product Discussion | Experience for unauthorized users | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic | Community Terms: phase 2 | Roadmap |  |  | 2024 Q3 | 30 | Digicampus, Humanity Hub, The Hague
| alkemio | Epic,Product Discussion | Community Invitations: Allowing inviting many (external) users at once | Roadmap |  |  | 2024 Q3 |  | VNG, Data Autonomy
| alkemio | Epic | InnovationHubs without networking updates | Roadmap |  | Custom Homepage (former Innovation Hubs) | 2024 Q2 | 30
| client-web | epic,client | Client: Developer documentation, roadmap | Roadmap |  |  | 2024 Q2 | 20
| alkemio | Epic | Dev env optimisation, incl InnovationHubs locally | Roadmap |  | Custom Homepage (former Innovation Hubs) | 2024 Q2
| alkemio | Epic | Smart Analytics to understand community needs/interests | Roadmap |  |  | 2024 Q2
| alkemio | Epic | Quota / resource management: Documents | Roadmap |  | Products + Licensing | 2024 Q2 | 30
| alkemio | Epic,Product Team | Contributor visibility | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic | User controls on data visibility | Roadmap |  |  | 2024 Q3
| alkemio | Epic,Product Discussion | Challenge/Opportunity refresh | Roadmap |  |  | 2024 Q2 | 50 | Digicampus
| alkemio | Epic | Bucket: Innovation Library Management, InnovationPack extensions | Roadmap |  |  | 2024 Q2 | 30
| alkemio | Epic,A: Platform | Innovation Hubs: Rounding out Functionality | Roadmap |  | Custom Homepage (former Innovation Hubs) | 2024 Q2 | 50 | Digicampus
| alkemio | Epic,Product Team,A: Platform | Branding at platform level | Roadmap |  | Custom Homepage (former Innovation Hubs) | 2024 Q3 | 30 | Digicampus
Valentin Yanakiev | alkemio | Epic | Operations: Kratos Administration | Roadmap |  |  | 2024 Q2 | 20
| alkemio | Epic,server | Technical debt: Tags/Innovation flow template functionality redesign | Roadmap |  |  | 2024 Q2
| alkemio | Epic,QA | Performance + scalability testing | Roadmap |  |  | 2024 Q3 | 30
| alkemio | Epic | Search results validated in service | Roadmap |  | Search: Smart | 2024 Q3 | 30
Valentin Yanakiev | infrastructure-operations | security,Epic | Security: Secret management | Roadmap |  |  | 2024 Q3 | 20
| alkemio | Epic,Product Team | Space Visualization component | Roadmap |  |  | 2024 Q3 | 30
| alkemio | Epic | Security: Control of provider per organization | Roadmap |  |  | 2024 Q3 | 50
| alkemio | Epic | Ecosystem Analytics: prototype | Roadmap |  | Connectivity Graph | 2024 Q3 | 80
| alkemio | Epic,Product Discussion | Innovation Flow: Lifecycles v2 | Roadmap |  |  | 2024 Q2 | 30
René Honig,Valentin Yanakiev | alkemio | Epic | Security: Kubernetes hardening | Roadmap |  |  | 2024 Q2 | 50
| alkemio | Epic | Handling of Time | Roadmap |  |  | 2024 Q3 | 30 |  | 10
Valentin Yanakiev | alkemio | Epic,Product Discussion | Error Handling: Presentation improvements | Roadmap |  |  | 2024 Q3 | 30
René Honig,Valentin Yanakiev | hub | Epic,operations | Security: Client code execution / injection | Roadmap |  |  | 2024 Q3 | 30
| alkemio | Epic,A: Community,Roadmap Discussion | Improved signup flow: Newsletter registration, GDPR, .. | Roadmap |  | User Engagement with the platform | 2024 Q3 | 20
| alkemio | Epic,Security | Security headers hardening | Roadmap |  |  | 2024 Q3 | 10
| alkemio | Epic | Search: richer data | Roadmap |  | Search: Smart
| alkemio | Epic | My Dashboard: live | Roadmap |  |  | 2024 Q2
| alkemio | Epic | Licensing: Payment flows (Wingback), upgrade | Roadmap |  | Create your own Space: GA
| alkemio | Epic,Atlas Team | Authorization: acting on behalf of | Roadmap |  |  | 2024 Q2
| alkemio | Epic | New Callout type (partner preference) | Roadmap |  | Richer interaction inside the Space | 2024 Q3
| alkemio | Epic | Richer and visible interactions in Space | Roadmap | 2025-10-14 |  | 2024 Q2 | 30