## Parameters
Capacity planning for Alkemio
This tab provides teams' velocity and overall releases capacity overview based on the current version of 2015 release calendar.
Sprint Start Date: | 2023-01-31
Current Sprint: | 56
Time Period | Time Period End | Features allocation, % | Development Sprints available | Points / sprint | Capacity | Comments
2023 Q1 | 2023-03-28 | 70% | 4 | 200 | 560
2023 Q2 | 2023-06-30 | 60% | 6.5 | 200 | 780
2023 Q3 | 2023-09-30 | 50% | 6.5 | 200 | 650
2023 Q4 | 2023-12-31 | 50% | 7 | 200 | 700
2024 | 2024-12-31 | 50% | 26.5 | 200 | 2650
Formulas:
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM(B3,1))/2
Development Sprints available = (WEEKNUM([Time Period End],1)-WEEKNUM([Time Period End, row above],1))/2

## Capacity
Delivery | Planned | Available | Functionality: enhancements | Functionality: new | Maintenance | Security | Performance | Functionality: Strategic | Not specified
2023 Q1 | 730 | 560 | 60 | 210 | 200 | 20 | 30 | 210 | 0
2023 Q2 | 900 | 780 | 90 | 400 | 70 | 80 | 0 | 260 | 0
2023 Q3 | 80 | 650 | 0 | 0 | 0 | 80 | 0 | 0 | 0
2023 Q4 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GITHUB_EPICS
Repository | Labels | Title | Status | Type | Period | EpicPoints | Partner | Sprint | Assignees | SprintPoints | Release
alkemio | T: User Engagment,Initiative | I: Innovation Spaces | Initiative | Functionality: new
alkemio | Epic | Calendar Events per community | Done | Functionality: new | 2023 Q1 | 50 | UWV | 2023-01-17
alkemio | Epic | User to user communication via notifications | In progress | Functionality: new | 2023 Q1 | 80 | UWV |  | Aleksandar Stojanovic | 60
alkemio | Epic | Reporting: Northstar Metric | In progress | Functionality: Strategic | 2023 Q1 | 50 |  | 2023-01-31 | Svetoslav Petkov | 30 | Release 230208
alkemio | Epic | UX Refinements: Round 2 | Done | Functionality: enhancements | 2023 Q1 | 30 |  | 2023-01-03 |  | 30
alkemio | Epic,UX | Platform Home page | In progress | Functionality: Strategic | 2023 Q1 | 50 |  | 2023-01-31 | Andrew Pazniak | 30
alkemio | Epic | UX Refinements - Round 3 | Defined | Functionality: enhancements | 2023 Q1 | 30 |  | 2023-01-31 |  | 40
alkemio | Epic | Capacity Planning | Done | Maintenance | 2023 Q1 | 10 |  | 2023-01-31 |  | 10
alkemio | Epic,UX | Innovation Spaces v1 | Being defined | Functionality: Strategic | 2023 Q1 | 80 | UWV |  |  | 10
alkemio | Epic | Calendar Events V2 | Being elaborated | Functionality: new | 2023 Q1 | 30 | UWV | 2023-02-14
infrastructure-operations | operations,Epic,Infrastructure | Security: Authentication via Microsoft identities - basic | Defined | Security | 2023 Q1 | 20 |  | 2023-02-14 | Rene Honig,Valentin Yanakiev | 20
alkemio | Epic,UX,client | Search: Within a Hub | Being elaborated | Functionality: new | 2023 Q1 | 20 | UWV, VNG | 2023-02-14
alkemio | Epic | Community forum on the platform | Defined | Functionality: new | 2023 Q1 | 30 |  | 2023-02-14 | Svetoslav Petkov | 10
alkemio | Epic | Naming alignment | Being elaborated | Maintenance | 2023 Q1 | 30 |  | 2023-02-14 | Valentin Yanakiev
alkemio | Epic | Handling of Time | Being elaborated | Maintenance | 2023 Q1 | 20 |  | 2023-02-14
alkemio | Epic,Infrastructure | Demo onto production | Being defined | Maintenance | 2023 Q1 | 50
alkemio | Epic,UX | UX Refinements - Round 4 | Being elaborated | Functionality: enhancements | 2023 Q1 | 30
alkemio | Epic,UX | Contributor visibility | Defined | Functionality: new | 2023 Q2 | 30 |  |  | Andrew Pazniak
alkemio | Epic,UX | Contribute Page | Being elaborated | Functionality: new | 2023 Q1 | 50
alkemio | Epic | Whiteboard: Usability | Being elaborated | Functionality: enhancements | 2023 Q2 | 30
alkemio | Epic,UX | Hub visibility for unauthorized users | Being elaborated | Functionality: new | 2023 Q2 | 30
server | Epic,server | Server domain model refinements | Being elaborated | Maintenance | 2023 Q1 | 50
alkemio | Epic | Release mgmt: Documentation, process + split | Being elaborated | Maintenance | 2023 Q1 | 50
alkemio | Epic | Error Handling: Presentation improvements | Being elaborated | Functionality: enhancements | 2023 Q2 | 30 |  |  | Valentin Yanakiev
alkemio | Epic | Whiteboard: interactive multi-user editing | Being elaborated | Functionality: Strategic | 2023 Q2 | 80 |  |  |  | 20
alkemio | Epic | Community: Terms per Hub | Icebox | Functionality: Strategic | 2023 Q2 | 50
alkemio | Epic | Documents: Wider usage, Management and limits | Icebox | Functionality: new | 2023 Q2 | 50
alkemio | Epic | Documents: Storage with privacy | Icebox | Functionality: new | 2023 Q2 | 50
alkemio | Epic | Accessibility + keyboard navigation | Icebox | Functionality: new | 2023 Q2 | 50
alkemio | Epic | Performance: Dataloaders / field resolvers | Being elaborated | Performance | 2023 Q1 | 30 |  |  |  | 30
alkemio | Epic,UX | Comments: Improved interaction | Icebox | Functionality: enhancements | 2023 Q2 | 30
alkemio | Epic,UX | Library: Innovation Pack management + usage | Parked | Functionality: new | 2023 Q2 | 50 |  |  | Svetoslav Petkov
alkemio | Epic | Security: Kubernetes hardening | Icebox | Security | 2023 Q2 | 50 |  |  | Rene Honig,Valentin Yanakiev
alkemio | Epic | Security: Control of provider per organization | Icebox | Security | 2023 Q3 | 50
alkemio | Epic | Infrastructure: Maintainability | Icebox | Maintenance | 2023 Q2 | 50
alkemio | Epic | Login Refinements / Kratos | Icebox | Security | 2023 Q2 | 30
hub | Epic,operations | Security: Client code execution / injection | Icebox | Security | 2023 Q3 | 30 |  |  | Rene Honig,Valentin Yanakiev
alkemio | Epic,UX | Grouping of Hubs by theme | Being elaborated | Functionality: Strategic | 2023 Q1 | 30
alkemio | Epic,UX | Invitations to Hub | Parked | Functionality: new | 2023 Q2 | 50 |  |  | Denise Larsson
alkemio | Epic | Reporting: Sharing of analysis | Parked | Maintenance | 2023 Q2 | 20
alkemio | Epic,UX | Hub Visualization component | Parked | Functionality: new | 2023 Q2 | 30
alkemio | Epic | Ecosystem Analytics: prototype | New | Functionality: Strategic | 2023 Q2 | 80
alkemio | Epic | Visuals on Journeys: Enhanced selection + search with alternative text | New | Functionality: new | 2023 Q2 | 30 | Envision |  | Carlos Cano
alkemio | Epic | Image upload + storage | New | Functionality: new | 2023 Q2 | 30
alkemio | Epic | Differentiation between journeys | New | Functionality: Strategic | 2023 Q2 | 50
alkemio | Epic | Matrix adapter as a separate service | Done | Maintenance | 2023 Q1 | 50 |  | 2023-01-03 |  | 40
alkemio | Epic | Private challenges | Done | Functionality: new | 2023 Q1 | 50 |  | 2023-01-03 | Neil Smyth | 30